## ProjectTeam
Name | GitHub Alias
Hager Magdub | magdh1
Antoni Tomic | tomia1
Roberto Tangarife | tange1
Ludovic Frehner | Arilar
Massah Hamidi | hamim1
Luca Ramos | ramol1

## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1 | Admit new patient information | New patient information have to be fed to the database | medium | 5h | 0h | 0h | waiting
2 | Admit new institutions | New institutions have to be added to the database | medium | 5h | 0h | 0h | waiting
3 | Admit new treatments | New treatments have to be added to the database | medium | 5h | 0h | 0h | waiting
4 | Create statistics according to new / existing patients | Statistics to get the information of the new / existing patients | medium | 40h | 10h | 0h | waiting
5 | Create statistics according to new / existing institutions | Statistics to get the information of the new / existing institutions | medium | 40h | 10h | 0h | waiting
6 | Create statistics according to new / existing treatments | Statistics to get the information of the new / existing treatments | medium | 40h | 10h | 0h | waiting
7 | create GUIs for all Menus | All menues have to be created | high | 20h | 50h | 50h | working
8 | Database | Database has to be connected and persistence implemented | high | 20h | 60h | 60h | working
9 | Vaadin has to work | Vaadin has to work on all groupmembers machines | high | 10h | 40h | 40h | done

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Reviewer | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1.1 | 2 | GUI | GUI needs to be designed (on paper) | UI | Antoni | Hager | medium | 3 | 6 | 6 | done | Sprint | Time
1.2 | 1 | Login | UI for Login | UI | Roberto | Luca | high | 1 | 2 | 2 | done | 1 | 21
1.3 | 1 | Login | Controller for Login | UI, Controller | Massah | Ludovic | high | 4 | 6 | 6 | done | 2 | 67
1.4 | 1 | Login | test of funcitonality | UI, Controller, Model | Luca | Roberto | high | 4 | 6 | 6 | done | 3 | 31
1.5 | 1 | Home-view | UI for Home-view | UI | Ludovic | Antoni | high | 7 | 7 | 7 | done
2.1 | 2 | Functionality | Vaadin has to work on all Laptops (Eclipse) | Eclipse | Antoni | Hager | high | 12 | 30 | 35 | done
2.2 | 2 | Database | Connection to database established | Eclipse, Database | Ludovic | Luca | high | 5 | 5 | 10 | done
2.3 | 2 | GUI | UI for Hospital | Eclipse, Vaadin | Antoni | Hager | high | 4 | 6 | 8 | done
2.4 | 2 | GUI | UI for Patient | Eclipse, Vaadin | Roberto | Luca | high | 4 | 6 | 4 | working
2.5 | 2 | GUI | UI for Addictions | Eclipse, Vaadin | Massah | Ludovic | high | 4 | 6 | 4 | working
2.6 | 3 | GUI | UI for Treatment | Eclipse, Vaadin | Luca | Roberto | high | 4 | 6 | 8 | done
2.7 | 3 | GUI | UI for statistics | Eclipse, Vaadin | Ludovic | Antoni | high | 4 | 6 | 6 | working
3.1 | 3 | Code | calculate data button implemented | Eclipse, Vaadin | Ludovic | Antoni | high | 3 | 3 | 3 | done
3.2 | 3 | Database | Persistence | Eclipse, Database | Luca | Massah | high | 6 | 10 | 14 | working

## BurndownChart
Sprint | Time of Record | Remaining Effort | Remaining Ressources
1 | 2016-12-02 | 15 | 0
2 | 2016-12-09 | 36 | 70
3 | 2016-12-23 | 60 | 60