## ProjectTeam
Name | GitHub Alias
Hager Magdub | magdh1
Antoni Tomic | tomia1
Roberto Tangarife | tange1
Ludovic Frehner | Arilar
Massah Hamidi | hamim1
Luca Ramos | ramol1

## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1 | Admit new patient information | New patient information have to be fed to the database | low | 40h | 0h | 0h | waiting
2 | Admit new institutions | New institutions have to be added to the database | medium | 40h | 0h | 0h | waiting
3 | Admit new treatments | New treatments have to be added to the database | medium | 40h | 0h | 0h | waiting
4 | Create statistics according to new / existing patients | Statistics to get the information of the new / existing patients | high | 20h | 0h | 0h | waiting
5 | Create statistics according to new / existing institutions | Statistics to get the information of the new / existing institutions | high | 20h | 0h | 0h | waiting
6 | Create statistics according to new / existing treatments | Statistics to get the information of the new / existing institutions | high | 20h | 0h | 0h | waiting

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Reviewer | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1.1 | 1 | GUI | GUI needs to be designed (on paper) | UI | Antoni | Hager | medium | 3 | 0 | 0 | waiting
1.2 | 1 | Login | UI for Login | UI | Roberto | Luca | high | 1 | 0 | 0 | waiting
1.3 | 1 | Login | Controller for Login | UI, Controller | Massah | Ludovic | high | 4 | 0 | 0 | waiting
1.4 | 1 | Login | test of funcitonality | UI, Controller, Model | Luca | Roberto | high | 1 | 0 | 0 | waiting
1.5 | 1 | Home-view | UI for Home-view | UI | Ludovic | Antoni | high | 3 | 0 | 0 | waiting

## BurndownChart
Sprint | Time of Record | Remaining Effort | Remaining Ressources
1 | 2016-12-02 | 36 | 36